## Slide 1: 60 Day Assessments
“OACCD initiative – Completing Needs Assessments within 60 days from admission,
Analysis to Implementation”

## Slide 2: Objective
Assessments within 60 days of New Admissions
  OAR - Risk Assessments https://oregon.public.law/rules/oar_291-078-0020
  OAR – Case Planning https://oregon.public.law/rules/oar_291-078-0026
Notes: At

## Slide 3: Administrative Analysis
  Josephine County prioritized the completion of a needs assessment and case plan on new cases within 60 days from admission, (February 4th, 2022)
  LSCMI & WRNA averaged about 75 days for completion, at that time
  Began with a timeline analysis, tracked 15-20 cases from sentencing to LSCMI completion
  Several points of consistent delay were identified
Notes: At

## Slide 4: Administrative Analysis
  Group intake was being scheduled out 14-21 days on average
  PO’s had “intake appointments” but time wasn’t protected, PO’s were often “re-scheduling” the LSCMI for 2-3 weeks out.
  Philosophical adjustment was needed regarding rapport building.
Notes: At

## Slide 5: Staff Analysis
  A Case Management Training was developed to facilitate a staff analysis on 2/9/22
  Lesson Plan was followed to guide the staff analysis with an emphasis on the following
    Communicate objective
    Answer the Question – WHY?
    Office visit Progression
    What is working?
    Barriers
    Strategies
Notes: At

## Slide 6: Results of Staff Analysis
  Findings and strategies from staff analysis were summarized and emailed to staff:
  Established Standards and Objectives
  What is working for us now
  Current & Potential Barriers
  Solutions
  Action Steps
Notes: At

## Slide 7: Operational Considerations
  Increase number of group intake days per week.
  Kept the number of intake groups the same but increase the volume of participants by adding an additional certified staff member and a case specialist (for administrative efficiency).
  See Office Visit Progression
Notes: At

## Slide 8
Notes: At

## Slide 9: Ongoing Analysis
  Use OMS to track assessments – (New, Overdue, Completed)
  Group intake list* with status. Weekly follow up by Lead PO
  Quarterly caseload reviews* prepared by Lead PO with Supervisor oversight
  DOC statewide, 60 day, LSCMI / WRNA emails
    Operational
    Not Done/Pending
  Dashboards* provided on OACCD website
    “Assessments within 60 Days of New Admission”
Notes: At

## Slide 11: Considerations for Implementation
  Jurisdictionally relevant solutions – not a one size fits all intervention
  Philosophy of assessment application
  Consistent monitoring until fundamental tasks are re-prioritized.
  Push back – considerable amounts coming.
Notes: At

## Slide 12: Future Considerations
  Case planning
Notes: At